## WBS
WORK BREAKDOWN STRUCTURE
Features/sub features |  | Description | Wireframe and Design | Wireframe and Design | Test ( day) | Test ( day) | FE ( day) | FE ( day) | BE ( day) | BE ( day) | PM (day) | PM (day) | Total | Note | Release plan
Extension
Send mail | Connect to google sheet |  | 1 | 0.5 | 1 | 0.5 | 2 | 1 | 5.5 | 2.75 | 2 | 1 | 5.25
| Connect to campain |  | 1.5 | 0.75 | 1.5 | 0.75 | 2 | 1 | 4 | 2 | 2 | 1 | 4.75
| Manage campain (CSM) |  | 1.5 | 0.75 | 1.5 | 0.75 | 3 | 1.5 | 4.5 | 2.25 | 1 | 0.5 | 5
| Manage email form file CSV (CSM) |  | 1.5 | 0.75 | 1.5 | 0.75 | 3 | 1.5 | 4.5 | 2.25 | 1.5 | 0.75 | 5.25
| Get email form upload CSV |  | 1 | 0.5 | 1.8 | 0.9 | 2 | 1 | 2.5 | 1.25 | 0.5 | 0.25 | 3.4
| Get email of google sheet |  | 1 | 0.5 | 1.8 | 0.9 | 2.5 | 1.25 | 3.5 | 1.75 | 1 | 0.5 | 4.4
| Get email of campain |  | 1 | 0.5 | 1.5 | 0.75 | 2 | 1 | 3 | 1.5 | 1 | 0.5 | 3.75
| Set UI Button Extension to component of gmail on website |  | 1.3 | 0.65 | 1 | 0.5 | 1.3 | 0.65 | 3 | 1.5 | 1 | 0.5 | 3.15
| Pop up Success when sent email |  | 0.6 | 0.3 | 0.5 | 0.25 | 2 | 1 | 3 | 1.5 | 1 | 0.5 | 3.25
| Send to mail test |  | 0.8 | 0.4 | 0.5 | 0.25 | 2.5 | 1.25 | 3.5 | 1.75 | 2 | 1 | 4.25
| List all mail test sent |  | 1 | 0.5 | 1.8 | 0.9 | 2.5 | 1.25 | 3 | 1.5 | 1 | 0.5 | 4.15
| Add label to gmail |  | 0.6 | 0.3 | 1.5 | 0.75 | 0 | 0 | 3.5 | 1.75 | 2.5 | 1.25 | 3.75
Mail Template | Manage mail template systems (CSM) |  | 1 | 0.5 | 2 | 1 | 2 | 1 | 5 | 2.5 | 3 | 1.5 | 6
| Select mail template |  | 1.2 | 0.6 | 1.8 | 0.9 | 2.5 | 1.25 | 3.5 | 1.75 | 2.5 | 1.25 | 5.15
| Change mail template by HTML |  | 1 | 0.5 | 1.8 | 0.9 | 2 | 1 | 2.5 | 1.25 | 1 | 0.5 | 3.65
| Create mail template by ChatGPT |  | 1 | 0.5 | 0.5 | 0.25 | 3 | 1.5 | 3.5 | 1.75 | 2 | 1 | 4.5
| Add label to gmail |  | 1 | 0.5 | 1.2 | 0.6 | 0 | 0 | 3.5 | 1.75 | 2 | 1 | 3.35
Personalize | Setup name type with Link |  | 1.2 | 0.6 | 1.8 | 0.9 | 2 | 1 | 4 | 2 | 2.5 | 1.25 | 5.15
| Manager name type |  | 2 | 1 | 1.2 | 0.6 | 1.5 | 0.75 | 3 | 1.5 | 1 | 0.5 | 3.35
| Manager link with name type |  | 2 | 1 | 1.5 | 0.75 | 2 | 1 | 3 | 1.5 | 1 | 0.5 | 3.75
Settings | Tracking open email |  | 2 | 1 | 1.8 | 0.9 | 1 | 0.5 | 5 | 2.5 | 2.5 | 1.25 | 5.15
| Tracking clicks link on email |  | 2 | 1 | 1.2 | 0.6 | 1 | 0.5 | 5 | 2.5 | 2.5 | 1.25 | 4.85
| Manager tracking systems (CSM) |  | 1.5 | 0.75 | 2 | 1 | 1 | 0.5 | 6 | 3 | 3 | 1.5 | 6
Action | Send mail |  | 1.5 | 0.75 | 1.5 | 0.75 | 1 | 0.5 | 3.5 | 1.75 | 1 | 0.5 | 3.5
| Create draft mail |  | 1.5 | 0.75 | 1.5 | 0.75 | 2 | 1 | 3.5 | 1.75 | 1 | 0.5 | 4
| Manage draft mail (CSM) |  | 3 | 1.5 | 2 | 1 | 5 | 2.5 | 6 | 3 | 2.5 | 1.25 | 7.75
Auto follow up | Set follow up mail |  | 3 | 1.5 | 2 | 1 | 2 | 1 | 4 | 2 | 2 | 1 | 5
| Set case(4 case ) for mail |  | 3 | 1.5 | 2.5 | 1.25 | 2.5 | 1.25 | 5 | 2.5 | 2.5 | 1.25 | 6.25
| Set time for mail ( Day , Time ) |  | 3 | 1.5 | 2.5 | 1.25 | 2 | 1 | 5.5 | 2.75 | 1 | 0.5 | 5.5
| Set message for mail |  | 2.5 | 1.25 | 3 | 1.5 | 3 | 1.5 | 6 | 3 | 3 | 1.5 | 7.5
| Manager follow up emails ( CSM) |  | 1 | 0.5 | 4 | 2 | 2.5 | 1.25 | 6 | 3 | 3 | 1.5 | 7.75
| Set State for mail |  | 1 | 0.5 | 2.5 | 1.25 | 5 | 2.5 | 6 | 3 | 3 | 1.5 | 8.25
| Add label to gmail |  | 1 | 0.5 | 2.5 | 1.25 | 0 | 0 | 3.5 | 1.75 | 1 | 0.5 | 3.5
| Manage auto follow up systems (CSM) |  | 3 | 1.5 | 3.5 | 1.75 | 2.5 | 1.25 | 6 | 3 | 3 | 1.5 | 7.5
Schedule | Set up Now Time |  | 2 | 1 | 2.5 | 1.25 | 2 | 1 | 4 | 2 | 1.5 | 0.75 | 5
| Set up in 5 minutes |  | 2 | 1 | 0.5 | 0.25 | 2 | 1 | 5 | 2.5 | 2.5 | 1.25 | 5
| Set in 1 hour |  | 2 | 1 | 0.5 | 0.25 | 2 | 1 | 4 | 2 | 1.5 | 0.75 | 4
| Set in 3 hours |  | 2 | 1 | 0.5 | 0.25 | 2 | 1 | 4 | 2 | 1.5 | 0.75 | 4
| Set tomorrow morning at 8 am |  | 2 | 1 | 0.5 | 0.25 | 2 | 1 | 4 | 2 | 1.5 | 0.75 | 4
| Set afternoon morning at 1 pm |  | 2 | 1 | 0.5 | 0.25 | 2 | 1 | 4 | 2 | 1.5 | 0.75 | 4
| Set evening morning at 8 am |  | 2 | 1 | 0.5 | 0.25 | 2 | 1 | 4 | 2 | 1.5 | 0.75 | 4
| Set Custom time ( date and hour) |  | 2 | 1 | 1.5 | 0.75 | 2 | 1 | 4 | 2 | 1.5 | 0.75 | 4.5
| Set Skip holiday |  | 1.5 | 0.75 | 1.2 | 0.6 | 2 | 1 | 5 | 2.5 | 2 | 1 | 5.1
| Manage holiday (CSM) |  | 2 | 1 | 3 | 1.5 | 2.5 | 1.25 | 5.5 | 2.75 | 2.5 | 1.25 | 6.75
| Set day of week( 7 days) |  | 2 | 1 | 1 | 0.5 | 1 | 0.5 | 5.5 | 2.75 | 2.5 | 1.25 | 5
| Set email per day |  | 2 | 1 | 1 | 0.5 | 1 | 0.5 | 6 | 3 | 3 | 1.5 | 5.5
| Set repeat email ( days) |  | 2 | 1 | 1 | 0.5 | 1 | 0.5 | 5.5 | 2.75 | 1.5 | 0.75 | 4.5
| Add label to gmail |  | 1.5 | 0.75 | 2 | 1 | 2 | 1 | 6 | 3 | 3 | 1.5 | 6.5
| Manage Schedule systems (CSM ) |  | 2 | 1 | 2.5 | 1.25 |  | 0 | 6 | 3 | 3 | 1.5 | 5.75
Advanced | Send as new email |  | 2 | 1 | 2 | 1 | 1.5 | 0.75 | 4.5 | 2.25 | 1.5 | 0.75 | 4.75
| Send as replies |  | 2 | 1 | 2 | 1 | 1.5 | 0.75 | 4.5 | 2.25 | 1.5 | 0.75 | 4.75
| Set account for multisend |  | 2 | 1 | 1 | 0.5 | 1 | 0.5 | 6 | 3 | 3 | 1.5 | 5.5
| List account for multisend |  | 2 | 1 | 1 | 0.5 | 3.5 | 1.75 | 6 | 3 | 3 | 1.5 | 6.75
| Link account for multisend |  | 2 | 1 | 1 | 0.5 | 3.5 | 1.75 | 6 | 3 | 3 | 1.5 | 6.75
| Set check email before send |  | 2.5 | 1.25 | 1.5 | 0.75 | 1.5 | 0.75 | 5 | 2.5 | 2.5 | 1.25 | 5.25
| Verify the email recipient's email format |  | 2.5 | 1.25 | 2.5 | 1.25 | 1 | 0.5 | 5 | 2.5 | 2.5 | 1.25 | 5.5
| Set up reply |  | 2.5 | 1.25 | 2.5 | 1.25 | 2 | 1 | 5.5 | 2.75 | 3 | 1.5 | 6.5
| Set up skip email ( email of campain) |  | 2.5 | 1.25 | 1.5 | 0.75 | 3 | 1.5 | 5.5 | 2.75 | 3 | 1.5 | 6.5
| Set poll to email |  | 2.5 | 1.25 | 1.5 | 0.75 | 1 | 0.5 | 5 | 2.5 | 1.5 | 0.75 | 4.5
| Set up preview text |  | 2.5 | 1.25 | 1.5 | 0.75 | 1 | 0.5 | 6 | 3 | 3 | 1.5 | 5.75
| Manage Advanced systems (CSM) |  | 2.5 | 1.25 | 2.5 | 1.25 | 1 | 0.5 | 6 | 3 | 3 | 1.5 | 6.25
Total Man/ Day |  |  | 108.7 | 54.35 | 99.4 | 49.7 | 117.3 | 58.65 | 280 | 140 | 123.5 | 61.75 | 310.1

## Estimation
Rate card
Office day |  | 20 | Days per month
Monthly Cost |  | 1905.7121 | Per person per month
|  |  | Total cost: | 30281.7656
Detail cost by development activities
# | Daj ao | Work Package | Efforts (Office-day) | Cost by activities | Discount price
1 |  | Requirement definition・Design・System analysis | 54.35 | 8696
2 |  | Implementation | 140 | 30100
3 |  | Test | 49.7 | 7455
4 |  | UAT support | 12 | 1200
5 |  | Project management | 61.75 | 15437.5
Total |  |  | 317.8 | 62888.5
|  | Total Man/ Month | 33
|  | Total INR/ Month | 5334403.813
|  | Exchange rate (USD - INR) | 84.8232

## Project Schedule
Project Team
Position |  | Person
Project Manager |  | 1
Business Analyst |  | 1
Developer |  | 8
Designer |  | 1
Q/A |  | 1
Project Schedule
Start | 2025-01-01
UAT | 2025-04-20
End | 2025-05-20